## RMP
Project Resource Management Planning
Project name: | Start Date: | End Date: | Time Duration: | Client: | Week:
- | 2026-01-02 | 2026-07-03 | 27 weeks | - | 2026-03-27
|  |  |  | Workhours by calendar | NL | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40
[6 empty] | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-07-01 |  |  | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 |  |  |  |  | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-02-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-03-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-07-01 |  |  | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01
[6 empty] | 2026-01-01: Weekly hours |  |  | Monthly hours | [10 empty] | Weekly cost | [28 empty] | Monthly Cost
Baseline/Forecast/Actual | Resource | Position | Discipline | Departament | blank | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Total hours | blank | 2026-01-30 | 2026-02-27 | 2026-03-27 | 2026-04-24 | 2026-05-29 | 2026-06-26 | 2026-07-03 | Total hours | blank | Rate/hr | blank | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | Total cost | blank | 2026-01-30 | 2026-02-27 | 2026-03-27 | 2026-04-24 | 2026-05-29 | 2026-06-26 | 2026-07-03 | Total cost
Baseline | Lina Maytum | Lead Process Engineer | Process | Engineering |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 1024 |  | 192 | 160 | 152 | 144 | 176 | 160 | 40 | 1024 |  | 100 |  | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 3200 | 4000 | 4000 | 3200 | 3200 | 4000 | 4000 | 3200 | 4000 | 3200 | 4000 | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 102400 |  | 19200 | 16000 | 15200 | 14400 | 17600 | 16000 | 4000 | 102400
Baseline | Rutger Claiden | Senior Mechanical Engineer | Mechanical | Engineering |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 20 | 20 | 20 | 20 | 804 |  | 192 | 160 | 152 | 124 | 76 | 80 | 20 | 804 |  | 50 |  | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1600 | 2000 | 2000 | 1600 | 1600 | 2000 | 1000 | 600 | 1000 | 600 | 1000 | 600 | 1000 | 1000 | 1000 | 1000 | 1000 | 40200 |  | 9600 | 8000 | 7600 | 6200 | 3800 | 4000 | 1000 | 40200
Baseline | Mavra Pandie | Instrumentation Engineer | Instrumentation | Engineering |  | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 16 | 8 | 8 | 16 | 16 | 8 | 16 | 8 | 16 | 8 | 16 | 16 | 16 | 0 | 0 | 344 |  | 72 | 64 | 56 | 48 | 56 | 48 | 0 | 344 |  | 40 |  | 320 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 320 | 640 | 640 | 320 | 320 | 640 | 640 | 320 | 640 | 320 | 640 | 320 | 640 | 640 | 640 | 0 | 0 | 13760 |  | 2880 | 2560 | 2240 | 1920 | 2240 | 1920 | 0 | 13760
Baseline | Constancy Van Halle | Senior Piping Engineer | Piping | Engineering |  | 24 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 32 | 32 | 24 | 24 | 32 | 32 | 24 | 32 | 24 | 32 | 24 | 16 | 16 | 16 | 16 | 0 | 712 |  | 152 | 128 | 120 | 112 | 136 | 64 | 0 | 712 |  | 50 |  | 1200 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1200 | 1600 | 1600 | 1200 | 1200 | 1600 | 1600 | 1200 | 1600 | 1200 | 1600 | 1200 | 800 | 800 | 800 | 800 | 0 | 35600 |  | 7600 | 6400 | 6000 | 5600 | 6800 | 3200 | 0 | 35600
Baseline | Ashli Gaisford | Lead Structural Engineer | Structural | Engineering |  | 24 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 32 | 32 | 24 | 24 | 32 | 32 | 24 | 32 | 24 | 32 | 24 | 16 | 16 | 16 | 16 | 0 | 712 |  | 152 | 128 | 120 | 112 | 136 | 64 | 0 | 712 |  | 100 |  | 2400 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 2400 | 3200 | 3200 | 2400 | 2400 | 3200 | 3200 | 2400 | 3200 | 2400 | 3200 | 2400 | 1600 | 1600 | 1600 | 1600 | 0 | 71200 |  | 15200 | 12800 | 12000 | 11200 | 13600 | 6400 | 0 | 71200
Baseline | Minor Betton | Electrical Engineer | Electrical | Engineering |  | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 16 | 8 | 8 | 16 | 16 | 8 | 16 | 8 | 16 | 8 | 16 | 16 | 16 | 16 | 0 | 360 |  | 72 | 64 | 56 | 48 | 56 | 64 | 0 | 360 |  | 40 |  | 320 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 320 | 640 | 640 | 320 | 320 | 640 | 640 | 320 | 640 | 320 | 640 | 320 | 640 | 640 | 640 | 640 | 0 | 14400 |  | 2880 | 2560 | 2240 | 1920 | 2240 | 2560 | 0 | 14400
Baseline | Darren Gellibrand | HSE Engineer | HSE | Engineering |  | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 16 | 8 | 8 | 16 | 16 | 8 | 16 | 8 | 16 | 8 | 16 | 16 | 16 | 16 | 0 | 360 |  | 72 | 64 | 56 | 48 | 56 | 64 | 0 | 360 |  | 50 |  | 400 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 400 | 800 | 800 | 400 | 400 | 800 | 800 | 400 | 800 | 400 | 800 | 400 | 800 | 800 | 800 | 800 | 0 | 18000 |  | 3600 | 3200 | 2800 | 2400 | 2800 | 3200 | 0 | 18000
Baseline | Dulciana Peche | Procurement Specialist | Procurement | Procurement |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 1024 |  | 192 | 160 | 152 | 144 | 176 | 160 | 40 | 1024 |  | 50 |  | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1600 | 2000 | 2000 | 1600 | 1600 | 2000 | 2000 | 1600 | 2000 | 1600 | 2000 | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 51200 |  | 9600 | 8000 | 7600 | 7200 | 8800 | 8000 | 2000 | 51200
Baseline | Alejoa O'Heffernan | Contracts Engineer | Procurement | Procurement |  | 8 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 136 |  | 72 | 16 | 0 | 0 | 0 | 32 | 16 | 136 |  | 50 |  | 400 | 800 | 800 | 800 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 800 | 6800 |  | 3600 | 800 | 0 | 0 | 0 | 1600 | 800 | 6800
Baseline | Jayme Shufflebotham | Project Controls Lead | Project Controls | Non-engineering |  | 24 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 32 | 32 | 24 | 24 | 32 | 32 | 24 | 32 | 24 | 32 | 16 | 24 | 24 | 24 | 24 | 24 | 760 |  | 152 | 128 | 120 | 112 | 128 | 96 | 24 | 760 |  | 100 |  | 2400 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 2400 | 3200 | 3200 | 2400 | 2400 | 3200 | 3200 | 2400 | 3200 | 2400 | 3200 | 1600 | 2400 | 2400 | 2400 | 2400 | 2400 | 76000 |  | 15200 | 12800 | 12000 | 11200 | 12800 | 9600 | 2400 | 76000
Baseline | Aydan Kazimzade | Associate Cost Controller | Project Controls | Non-engineering |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 1024 |  | 192 | 160 | 152 | 144 | 176 | 160 | 40 | 1024 |  | 30 |  | 960 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 960 | 1200 | 1200 | 960 | 960 | 1200 | 1200 | 960 | 1200 | 960 | 1200 | 960 | 1200 | 1200 | 1200 | 1200 | 1200 | 30720 |  | 5760 | 4800 | 4560 | 4320 | 5280 | 4800 | 1200 | 30720
Baseline | Abbey McAllister | Project Admin | Information Management | Non-engineering |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 1024 |  | 192 | 160 | 152 | 144 | 176 | 160 | 40 | 1024 |  | 100 |  | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 3200 | 4000 | 4000 | 3200 | 3200 | 4000 | 4000 | 3200 | 4000 | 3200 | 4000 | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 102400 |  | 19200 | 16000 | 15200 | 14400 | 17600 | 16000 | 4000 | 102400
[5 empty] | Total | 264 | 360 | 360 | 360 | 360 | 360 | 344 | 344 | 344 | 344 | 256 | 344 | 344 | 256 | 256 | 344 | 324 | 236 | 324 | 236 | 324 | 228 | 284 | 284 | 300 | 284 | 220 | 8284 |  | 1704 | 1392 | 1288 | 1180 | 1348 | 1152 | 220 | 8284 |  |  |  | 18000 | 24080 | 24080 | 24080 | 24080 | 24080 | 23280 | 23280 | 23280 | 23280 | 17600 | 23280 | 23280 | 17600 | 17600 | 23280 | 22280 | 16600 | 22280 | 16600 | 22280 | 15800 | 19080 | 19080 | 19880 | 19240 | 15400 | 562680 |  | 114320 | 93920 | 87440 | 80760 | 93560 | 77280 | 15400 | 562680
Forecast | Lina Maytum | Lead Process Engineer | Process | Engineering |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 1024 |  | 192 | 160 | 152 | 144 | 176 | 160 | 40 | 1024 |  | 100 |  | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 3200 | 4000 | 4000 | 3200 | 3200 | 4000 | 4000 | 3200 | 4000 | 3200 | 4000 | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 102400 |  | 19200 | 16000 | 15200 | 14400 | 17600 | 16000 | 4000 | 102400
Forecast | Rutger Claiden | Senior Mechanical Engineer | Mechanical | Engineering |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 20 | 12 | 20 | 12 | 20 | 12 | 20 | 20 | 20 | 20 | 20 | 804 |  | 192 | 160 | 152 | 124 | 76 | 80 | 20 | 804 |  | 50 |  | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1600 | 2000 | 2000 | 1600 | 1600 | 2000 | 1000 | 600 | 1000 | 600 | 1000 | 600 | 1000 | 1000 | 1000 | 1000 | 1000 | 40200 |  | 9600 | 8000 | 7600 | 6200 | 3800 | 4000 | 1000 | 40200
Forecast | Mavra Pandie | Instrumentation Engineer | Instrumentation | Engineering |  | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 16 | 8 | 8 | 16 | 16 | 8 | 16 | 8 | 16 | 8 | 16 | 16 | 16 | 0 | 0 | 344 |  | 72 | 64 | 56 | 48 | 56 | 48 | 0 | 344 |  | 40 |  | 320 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 320 | 640 | 640 | 320 | 320 | 640 | 640 | 320 | 640 | 320 | 640 | 320 | 640 | 640 | 640 | 0 | 0 | 13760 |  | 2880 | 2560 | 2240 | 1920 | 2240 | 1920 | 0 | 13760
Forecast | Constancy Van Halle | Senior Piping Engineer | Piping | Engineering |  | 24 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 32 | 32 | 24 | 24 | 32 | 32 | 24 | 32 | 32 | 32 | 32 | 32 | 16 | 16 | 8 | 8 | 744 |  | 152 | 128 | 120 | 112 | 152 | 72 | 8 | 744 |  | 50 |  | 1200 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1200 | 1600 | 1600 | 1200 | 1200 | 1600 | 1600 | 1200 | 1600 | 1600 | 1600 | 1600 | 1600 | 800 | 800 | 400 | 400 | 37200 |  | 7600 | 6400 | 6000 | 5600 | 7600 | 3600 | 400 | 37200
Forecast | Ashli Gaisford | Lead Structural Engineer | Structural | Engineering |  | 24 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 32 | 32 | 24 | 24 | 32 | 32 | 24 | 32 | 24 | 32 | 24 | 16 | 16 | 16 | 8 | 8 | 712 |  | 152 | 128 | 120 | 112 | 136 | 56 | 8 | 712 |  | 100 |  | 2400 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 2400 | 3200 | 3200 | 2400 | 2400 | 3200 | 3200 | 2400 | 3200 | 2400 | 3200 | 2400 | 1600 | 1600 | 1600 | 800 | 800 | 71200 |  | 15200 | 12800 | 12000 | 11200 | 13600 | 5600 | 800 | 71200
Forecast | Minor Betton | Electrical Engineer | Electrical | Engineering |  | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 16 | 8 | 8 | 16 | 16 | 8 | 16 | 8 | 16 | 8 | 16 | 16 | 16 | 8 | 8 | 360 |  | 72 | 64 | 56 | 48 | 56 | 56 | 8 | 360 |  | 40 |  | 320 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 320 | 640 | 640 | 320 | 320 | 640 | 640 | 320 | 640 | 320 | 640 | 320 | 640 | 640 | 640 | 320 | 320 | 14400 |  | 2880 | 2560 | 2240 | 1920 | 2240 | 2240 | 320 | 14400
Forecast | Darren Gellibrand | HSE Engineer | HSE | Engineering |  | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 16 | 16 | 8 | 8 | 16 | 16 | 8 | 16 | 8 | 16 | 8 | 16 | 16 | 16 | 8 | 8 | 360 |  | 72 | 64 | 56 | 48 | 56 | 56 | 8 | 360 |  | 50 |  | 400 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 400 | 800 | 800 | 400 | 400 | 800 | 800 | 400 | 800 | 400 | 800 | 400 | 800 | 800 | 800 | 400 | 400 | 18000 |  | 3600 | 3200 | 2800 | 2400 | 2800 | 2800 | 400 | 18000
Forecast | Dulciana Peche | Procurement Specialist | Procurement | Procurement |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 32 | 32 | 32 | 32 | 32 | 984 |  | 192 | 160 | 152 | 144 | 176 | 128 | 32 | 984 |  | 50 |  | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1600 | 2000 | 2000 | 1600 | 1600 | 2000 | 2000 | 1600 | 2000 | 1600 | 2000 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 49200 |  | 9600 | 8000 | 7600 | 7200 | 8800 | 6400 | 1600 | 49200
Forecast | Alejoa O'Heffernan | Contracts Engineer | Procurement | Procurement |  | 8 | 16 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 16 | 136 |  | 72 | 16 | 0 | 0 | 0 | 32 | 16 | 136 |  | 50 |  | 400 | 800 | 800 | 800 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 800 | 6800 |  | 3600 | 800 | 0 | 0 | 0 | 1600 | 800 | 6800
Forecast | Jayme Shufflebotham | Project Controls Lead | Project Controls | Non-engineering |  | 24 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 24 | 32 | 32 | 24 | 24 | 32 | 32 | 24 | 32 | 24 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | 720 |  | 152 | 128 | 120 | 112 | 128 | 64 | 16 | 720 |  | 100 |  | 2400 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 2400 | 3200 | 3200 | 2400 | 2400 | 3200 | 3200 | 2400 | 3200 | 2400 | 3200 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 72000 |  | 15200 | 12800 | 12000 | 11200 | 12800 | 6400 | 1600 | 72000
Forecast | Aydan Kazimzade | Associate Cost Controller | Project Controls | Non-engineering |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 1024 |  | 192 | 160 | 152 | 144 | 176 | 160 | 40 | 1024 |  | 30 |  | 960 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 960 | 1200 | 1200 | 960 | 960 | 1200 | 1200 | 960 | 1200 | 960 | 1200 | 960 | 1200 | 1200 | 1200 | 1200 | 1200 | 30720 |  | 5760 | 4800 | 4560 | 4320 | 5280 | 4800 | 1200 | 30720
Forecast | Abbey McAllister | Project Information Manager | Information Management | Non-engineering |  | 32 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 32 | 40 | 40 | 32 | 32 | 40 | 40 | 32 | 40 | 32 | 40 | 32 | 40 | 40 | 40 | 40 | 40 | 1024 |  | 192 | 160 | 152 | 144 | 176 | 160 | 40 | 1024 |  | 100 |  | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 3200 | 4000 | 4000 | 3200 | 3200 | 4000 | 4000 | 3200 | 4000 | 3200 | 4000 | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 102400 |  | 19200 | 16000 | 15200 | 14400 | 17600 | 16000 | 4000 | 102400
[5 empty] | Total | 264 | 360 | 360 | 360 | 360 | 360 | 344 | 344 | 344 | 344 | 256 | 344 | 344 | 256 | 256 | 344 | 324 | 236 | 324 | 244 | 324 | 236 | 284 | 268 | 284 | 236 | 236 | 8236 |  | 1704 | 1392 | 1288 | 1180 | 1364 | 1072 | 236 | 8236 |  |  |  | 18000 | 24080 | 24080 | 24080 | 24080 | 24080 | 23280 | 23280 | 23280 | 23280 | 17600 | 23280 | 23280 | 17600 | 17600 | 23280 | 22280 | 16600 | 22280 | 17000 | 22280 | 16200 | 18680 | 17880 | 18680 | 16120 | 16120 | 558280 |  | 114320 | 93920 | 87440 | 80760 | 94360 | 71360 | 16120 | 558280
Actual | Lina Maytum | Lead Process Engineer | Process | Engineering |  | 2026-01-01: 32; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-03-01: 40; 2026-03-01: 32; 2026-03-01: 40; 2026-03-01: 40 | 504 |  | 192 | 160 | 152 | 0 | 0 | 0 | 0 | 504 |  | 100 |  | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 3200 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 |  | 19200 | 16000 | 15200 | 0 | 0 | 0 | 0 | 50400
Actual | Rutger Claiden | Senior Mechanical Engineer | Mechanical | Engineering |  | 2026-01-01: 32; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-03-01: 40; 2026-03-01: 32; 2026-03-01: 40; 2026-03-01: 40 | 504 |  | 192 | 160 | 152 | 0 | 0 | 0 | 0 | 504 |  | 50 |  | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1600 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 |  | 9600 | 8000 | 7600 | 0 | 0 | 0 | 0 | 25200
Actual | Mavra Pandie | Instrumentation Engineer | Instrumentation | Engineering |  | 2026-01-01: 8; 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-03-01: 16; 2026-03-01: 8; 2026-03-01: 16; 2026-03-01: 16 | 192 |  | 72 | 64 | 56 | 0 | 0 | 0 | 0 | 192 |  | 40 |  | 320 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 320 | 640 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7680 |  | 2880 | 2560 | 2240 | 0 | 0 | 0 | 0 | 7680
Actual | Constancy Van Halle | Senior Piping Engineer | Piping | Engineering |  | 2026-01-01: 24; 2026-01-01: 32; 2026-01-01: 32; 2026-01-01: 32; 2026-01-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-03-01: 32; 2026-03-01: 24; 2026-03-01: 32; 2026-03-01: 32 | 400 |  | 152 | 128 | 120 | 0 | 0 | 0 | 0 | 400 |  | 50 |  | 1200 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1600 | 1200 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 |  | 7600 | 6400 | 6000 | 0 | 0 | 0 | 0 | 20000
Actual | Ashli Gaisford | Lead Structural Engineer | Structural | Engineering |  | 2026-01-01: 24; 2026-01-01: 32; 2026-01-01: 32; 2026-01-01: 32; 2026-01-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-03-01: 32; 2026-03-01: 24; 2026-03-01: 32; 2026-03-01: 32 | 400 |  | 152 | 128 | 120 | 0 | 0 | 0 | 0 | 400 |  | 100 |  | 2400 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 2400 | 3200 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  | 15200 | 12800 | 12000 | 0 | 0 | 0 | 0 | 40000
Actual | Minor Betton | Electrical Engineer | Electrical | Engineering |  | 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-03-01: 16; 2026-03-01: 8; 2026-03-01: 16; 2026-03-01: 16 | 200 |  | 80 | 64 | 56 | 0 | 0 | 0 | 0 | 200 |  | 40 |  | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 640 | 320 | 640 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 |  | 3200 | 2560 | 2240 | 0 | 0 | 0 | 0 | 8000
Actual | Darren Gellibrand | HSE Engineer | HSE | Engineering |  | 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-02-01: 16; 2026-03-01: 16; 2026-03-01: 8; 2026-03-01: 16; 2026-03-01: 8 | 192 |  | 80 | 64 | 48 | 0 | 0 | 0 | 0 | 192 |  | 50 |  | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 400 | 800 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 |  | 4000 | 3200 | 2400 | 0 | 0 | 0 | 0 | 9600
Actual | Dulciana Peche | Procurement Specialist | Procurement | Procurement |  | 2026-01-01: 32; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-03-01: 40; 2026-03-01: 32; 2026-03-01: 40; 2026-03-01: 40 | 504 |  | 192 | 160 | 152 | 0 | 0 | 0 | 0 | 504 |  | 50 |  | 1600 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 1600 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25200 |  | 9600 | 8000 | 7600 | 0 | 0 | 0 | 0 | 25200
Actual | Alejoa O'Heffernan | Contracts Engineer | Procurement | Procurement |  | 2026-01-01: 8; 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-01-01: 16; 2026-02-01: 0; 2026-02-01: 0; 2026-02-01: 0; 2026-02-01: 0; 2026-03-01: 0; 2026-03-01: 0; 2026-03-01: 0; 2026-03-01: 0 | 72 |  | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 72 |  | 50 |  | 400 | 800 | 800 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 |  | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600
Actual | Jayme Shufflebotham | Project Controls Lead | Project Controls | Non-engineering |  | 2026-01-01: 24; 2026-01-01: 32; 2026-01-01: 32; 2026-01-01: 32; 2026-01-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-02-01: 32; 2026-03-01: 32; 2026-03-01: 24; 2026-03-01: 32; 2026-03-01: 32 | 400 |  | 152 | 128 | 120 | 0 | 0 | 0 | 0 | 400 |  | 100 |  | 2400 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 3200 | 2400 | 3200 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 |  | 15200 | 12800 | 12000 | 0 | 0 | 0 | 0 | 40000
Actual | Aydan Kazimzade | Associate Cost Controller | Project Controls | Non-engineering |  | 2026-01-01: 32; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-03-01: 40; 2026-03-01: 32; 2026-03-01: 40; 2026-03-01: 40 | 504 |  | 192 | 160 | 152 | 0 | 0 | 0 | 0 | 504 |  | 30 |  | 960 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 960 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15120 |  | 5760 | 4800 | 4560 | 0 | 0 | 0 | 0 | 15120
Actual | Abbey McAllister | Project Information Manager | Information Management | Non-engineering |  | 2026-01-01: 32; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-01-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-02-01: 40; 2026-03-01: 40; 2026-03-01: 32; 2026-03-01: 40; 2026-03-01: 40 | 504 |  | 192 | 160 | 152 | 0 | 0 | 0 | 0 | 504 |  | 100 |  | 3200 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 3200 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50400 |  | 19200 | 16000 | 15200 | 0 | 0 | 0 | 0 | 50400
[5 empty] | Total | 280 | 360 | 360 | 360 | 360 | 344 | 344 | 344 | 344 | 344 | 256 | 344 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4376 |  | 1720 | 1376 | 1280 | 0 | 0 | 0 | 0 | 4376 |  |  |  | 18720 | 24080 | 24080 | 24080 | 24080 | 23280 | 23280 | 23280 | 23280 | 23280 | 17600 | 23280 | 22880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295200 |  | 115040 | 93120 | 87040 | 0 | 0 | 0 | 0 | 295200

## Monthly Cost Report
Project Monthly Cost Report | [11 empty] | Cut-off: | 2026-03-27
Description |  | Budget |  | Period Actual |  | Actual to Date |  | Forecast at Completion |  | Forecast to Go |  | Budget Variance
|  | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost | Hours | Cost
Discipline | Process | 1024 | 102400 | 152 | 15200 | 504 | 50400 | 1024 | 102400 | 520 | 52000 | 0 | 0
| Mechanical | 804 | 40200 | 152 | 7600 | 504 | 25200 | 804 | 40200 | 300 | 15000 | 0 | 0
| Instrumentation | 344 | 13760 | 56 | 2240 | 192 | 7680 | 344 | 13760 | 152 | 6080 | 0 | 0
| Piping | 712 | 35600 | 120 | 6000 | 400 | 20000 | 744 | 37200 | 344 | 17200 | 32 | 1600
| Structural | 712 | 71200 | 120 | 12000 | 400 | 40000 | 712 | 71200 | 312 | 31200 | 0 | 0
| Electrical | 360 | 14400 | 56 | 2240 | 200 | 8000 | 368 | 14720 | 168 | 6720 | 8 | 320
| HSE | 360 | 18000 | 48 | 2400 | 192 | 9600 | 360 | 18000 | 168 | 8400 | 0 | 0
| Procurement | 1160 | 58000 | 152 | 7600 | 576 | 28800 | 1104 | 55200 | 528 | 26400 | -56 | -2800
| Project Controls | 1784 | 106720 | 272 | 16560 | 904 | 55120 | 1744 | 102720 | 840 | 47600 | -40 | -4000
| Information Management | 1024 | 102400 | 152 | 15200 | 504 | 50400 | 1024 | 102400 | 520 | 52000 | 0 | 0
| Total | 8284 | 562680 | 1280 | 87040 | 4376 | 295200 | 8228 | 557800 | 3852 | 262600 | -56 | -4880
Comments:

## Employee Hours Variance
Week-Ending: | 2026-03-27 | Employee Hours Variance by Week Forecast vs. Actual
Resource | Position | Discipline | Departament | Forecast | Actual | Delta | Comments
Lina Maytum | Lead Process Engineer | Process | Engineering | 40 | 40 | 0
Rutger Claiden | Senior Mechanical Engineer | Mechanical | Engineering | 40 | 40 | 0
Mavra Pandie | Instrumentation Engineer | Instrumentation | Engineering | 16 | 16 | 0
Constancy Van Halle | Senior Piping Engineer | Piping | Engineering | 32 | 32 | 0
Ashli Gaisford | Lead Structural Engineer | Structural | Engineering | 32 | 32 | 0
Minor Betton | Electrical Engineer | Electrical | Engineering | 16 | 16 | 0
Darren Gellibrand | HSE Engineer | HSE | Engineering | 16 | 8 | 8
Dulciana Peche | Procurement Specialist | Procurement | Procurement | 40 | 40 | 0
Alejoa O'Heffernan | Contracts Engineer | Procurement | Procurement | 0 | 0 | 0
Jayme Shufflebotham | Project Controls Lead | Project Controls | Non-engineering | 32 | 32 | 0
Aydan Kazimzade | Associate Cost Controller | Project Controls | Non-engineering | 40 | 40 | 0
Abbey McAllister | Project Information Manager | Information Management | Non-engineering | 40 | 40 | 0
|  |  | Total: | 344 | 336 | 8

## Calendar (hidden)
2026-01-02 | 2026-01-30
2026-01-09 | 2026-02-27
2026-01-16 | 2026-03-27
2026-01-23 | 2026-04-24
2026-01-30 | 2026-05-29
2026-02-06 | 2026-06-26
2026-02-13 | 2026-07-03
2026-02-20
2026-02-27
2026-03-06
2026-03-13
2026-03-20
2026-03-27
2026-04-03
2026-04-10
2026-04-17
2026-04-24
2026-05-01
2026-05-08
2026-05-15
2026-05-22
2026-05-29
2026-06-05
2026-06-12
2026-06-19
2026-06-26
2026-07-03